# TENDER  DOCUMENTS

SPECIAL  CONDITIONS  OF  CONTRACT

# PLD–CS049/26/33

The complementary conditions set forth in these special conditions are in addition to, or complement of, the relevant conditions and provisions provided for in the General Conditions of Contract.

Clause 10.5 Liquidated Damages for delay of work

Refer to Clause 18 of Technical Specification.

Clause 11.2 Fines/Penalties for Safety Non-Compliance

In the event of breaching environmental and safety obligations, the Contractor shall pay to CEM the penalties according to the latest version of “SHE Non-Compliance in Contract Managed by CEM”, and without prejudice to the right of CEM to claim the Contractor for indemnification due to such non-compliance.

Clause 11.2 Health, Safety and Security Rules (Insurance)

The Insurance shall cover all the risks of bodily harm or damage to CEM’s property or third parties.  Minimum insurance amount shall be MOP5,000,000.00 for any one accident/number of accidents unlimited.

List of CEM accepted insurers

- AIG Insurance Hong Kong Limited (Macau Branch)

- Asia Insurance Company Ltd.

- MSIG Insurance (Hong Kong) Ltd.

- China Taiping Insurance (Macau) Company Limited

- Luen Fung Hang Insurance Company Ltd.

- Macau Insurance Company Ltd.

- QBE General Insurance (Hong Kong) Ltd.

- Chubb Insurance Macau Limited

- Fidelidade Macau- Insurance Company Limited

- Berkshire Hathaway Specialty Insurance Company

- AXA General Insurance Hong Kong Limited

- The People’s Insurance Company of China (Hong Kong) Limited (Macau Branch)

# Clause 13	Defects Liability Period

Refer to Clause 17 of Technical Specification.

Clause 15	 Prices / Payment

Prices

The prices are as defined in the Contractual Price schedule and confirmed on the Letter of Acceptance.  They are firm prices.

Proposed prices are to be quoted, denominated and paid in any of the following currencies:

- Patacas

Payment

- 20% of the total Contract Price upon the Kick-off Meeting (confirmed by CEM’s issuance of Interim Certificate)

- 30% of the total Contract Price upon completion and submission of the Mid-Term Report (confirmed by CEM’s issuance of Interim Certificate)

- 40% of the total Contract Price upon completion and submission of the Final Report or Stage Report for the end of 2-year initial term  (confirmed by CEM’s issuance of Taking Over Certificate)

- 10% of the total Contract Price upon the end of 12 months Defects Liability Period after the issuance of the Taking Over Certificate (TOC) for the completion of consultancy service in the initial 2-year term, or the termination of subsequent consultancy services, whichever is later (confirmed by CEM’s issuance of Defects Liability Certificate)

The payment of Subsequent Consultant Services after Principal Consultancy Services (主顧問服務屆滿後的後續服務) and Alternative Consultant Services during the Construction Standby Period (施工真空期間的替代顧問服務) are to be paid monthly.

All payments should be settled within 45 days from the date of the issuance of the respective invoices; invoices to be submitted after obtaining the related certificates.

A copy of the Declaration Form and the latest Taxation Document (M/1, M/8) should be presented to CEM before any payment will be effected.  For newly established company, only the Form “M/1” (duly approved and stamped by the “Direcção dos Serviços de Finanças”) should be presented in the 1st year and the Form “M/8” (issued by the “Direcção dos Serviços de Finanças”) should be presented in the subsequent year.

Important Note

Based on the Macau Law 1/89M which was printed on "Boletim Oficial" no. 16, 17 Abril/89, those overseas Contractors without branch office in Macau are required to perform a Commercial Registration (submission of M/1 Declaration Form) at Repartição de Finanças of Direcção dos Serviços de Finanças (Finance Bureau of Macau).

The M1 application is a legal procedure which is by-law and must be done by the company itself.

For more details on the taxation legislation of the Macau SAR, please refer to the related government website by this link: http://www.dsf.gov.mo/ and the "Frequently Questions and Answers" area http://www.dsf.gov.mo/tax/tax_faq.aspx in their website.

For newly established company, only the Form “M/1” (duly approved and stamped by the “Direcção dos Serviços de Finanças”) should be presented in the 1st year and the Form “M/8” (issued by the “Direcção dos Serviços de Finanças”) should be presented in the subsequent year.

Occupational Safety Card issued by DSAL

Copies of “Construction Industry Occupational Safety Cards” issued by DSAL for the involved employees to be allocated for this project shall be submitted to CEM before work commencement on site.