________________________________________________________________________

G01-G04發電機退役及拆除工程 (DDD)

G01-G04 DECOMMISSIONING,

DEMOLITION, SITE REMEDIATION

AND DECONTAMINATION (DDD)

項目管理、現場拆卸工作安全、環境及質量控制與監督

Project Management, Demolition Site Works Safety, Environmental and Quality

Control & Supervision

顧問服務

Consultancy Services

________________________________________________________________________

目錄CONTENT

1.	項目簡介INTRODUCTION	3

2.	顧問服務範圍SCOPE OF CONSULTANCY SERVICES	5

3.	顧問的職責ROLES AND RESPONSIBILITIES	11

4.	顧問組織人員的要求PERSONNEL OF THE CONSULTANT ORGANIZATION	12

5.	現場及檢查Site and Inspection	13

6.	顧問的供給DELIVERABLES BY THE CONSULTANT	14

7.	機密性CONFIDENTIALITY	18

8.	規範與限制REGULATION AND RESTRICTION	18

9.	服務供給期DURATION OF SERVICES TO BE PROVIDED	18

10.	一般要求GENERAL REQUIREMENT	19

11.	合同期限與後續服務TERM AND SUBSEQUENT SERVICES	20

12.	施工真空期之處理Handling for the Construction Standby Period	20

13.	投標提交文件要求TENDER SUBMISSION REQUIREMENTS	21

14.	顧問服務期間需提交的文件DOCUMENTS TO BE SUBMITTED DURING THE CONSULTANTCY SERVICE	23

15.	投標強制要求Compulsory Requirement	24

16.	報價之有效期Validity of the Offers	25

17.	其他　MISCELLANEOUS	25

a)	安全預防措施　Safety Precaution	25

b)	財產保護Protection of the Properties	25

c)	合同語言Contractual Language	25

# 項目簡介INTRODUCTION

題述拆卸項目主要涉及路環發電廠A廠G01/02機組和G03/04機組，以及其關連的系統和A廠維修工場的退役、設備轉移及拆卸的工作。

The captioned demolition project mainly involves the works involves the decommissioning, relocation, dismantling and demolition of G01/G02 and G03/G04 power plants, their associated systems and CCA Maintenance Building at Coloane Power Station (CPS).

其中，大部分拆除的設施因多年服役使用已出現老化損壞，現狀狀況欠佳，在進行退役及拆卸工程期間，對工作人員存在潛在的安全風險，特別是來自戶外構件的部分。此外，該拆卸項目涉及的部分區域仍處於運作狀態。施工區域附近有不少現有設施需予以保留並繼續運作，包括燃油儲存罐及管道、消防系統、電力系統、儲/輸氨系統、供水系統等。

Most of the demolished facilities have been deteriorated over the years and are in poor condition, there are potential risks in terms of safety to personnel during the decommissioning and demolition work, especially from those outdoor components. Moreover, the demolition project involves parts of the areas to be still in operation. Some existing facilities in the vicinity of the work area nearly are to be retained and are still in service, which include fuel oil storage tanks and pipes, firefighting system, electrical power, ammonia storage/transportation, water supply systems, etc.

另一方面，考慮到施工區域可用空間有限，且緊鄰現正運作的關鍵設備，因此在執行本拆卸工程時須格外留意並採取額外預防措施，尤其因其位置緊貼燃油儲存罐及主消防泵，在拆卸G01/G02煙囪時需特別注意。

On the other hand, the constraint of limited space available for the work areas, which is very close to critical equipment that is in operation now, causes additional attention and extra caution during the execution of this demolition work especially during the demolition of G01/G02 stack which is just adjacent to the fuel oil storage tanks & the main firefighting pump.

該拆卸項目「 G01-G04 DECOMMISSIONING, DEMOLITION, SITE REMEDIATION AND DECONTAMINATION (DDD) (G01-G04發電機退役及拆除工程 (DDD)) 」及相關聯的土壤修復工作（以下稱「 該項目」），工作內容主要包括：

The output of the demolition project, named as, G01-G04 DECOMMISSIONING, DEMOLITION, SITE REMEDIATION AND DECONTAMINATION (DDD) and associated soil remediation works (Hereafter called “the Project”) will comprise the following:

- 設施的退役：

安全及有系統地實施路環發電廠A廠G01/02號及G03/04號發電機組的停運退役。

Decommissioning of Facilities:

Safe and systematic shutdown of CCA G01/G02 and G03/G04 power plants.

- 拆卸工作：

建築結構及設備的拆卸，涉及路環發電廠A廠G01/02號機組大樓及煙囪、G03/04號機組大樓及煙囪、維修工房、G01至04號機組加氯間和G01至04號機組海水泵房。

Demolition Activities:

Removal of structures and equipment, including: G01/G02 Engine Building & G01/G02 Stack, G03/G04 Engine Building & G03/G04 Stack, Maintenance Building, G01-G04 Chlorination Plant and G01-G04 CWP Pump House in CCA.

- 土壤修復：

定位及緩解現場污染，確保對相關環保規範的遵從。

Soil Remediation:

Addressing and mitigating contamination on-site, ensuring environmental compliance.

- 去污：

設施設備上危害物質的清除。

Decontamination Procedures:

Cleaning and removing hazardous substance from facilities and equipment.

- 安全措施：

建立安全制度，以保障人員和設備在項目執行期間的安全。

Safety Measures:

Implementing safe system to protect personnel and operational facilities during execution.

- 廢物管理：

妥善處理和管理在拆卸和修復工作中所產生的可回收廢棄物料、垃圾和危害廢物。

Waste Management:

Proper disposal and management of recyclable materials, debris and hazardous waste generated from demolition and remediation.

- 現場修復：

在拆卸及修復工作後復原現場至安全及穏定的狀態。

Restoration of Site:

Restoring the site to a safe and stable condition post-demolition and remediation.

- 條例及規範的遵從：

確保所有工作均合符本地相關法例和安全標準的要求。

Compliance with Regulations:

Ensuring all activities adhere to local regulations and safety standards.

該項目的工作內容請參閱附件（Annex）。

The contents of the works in the Project can refer to the Annex.

基於上述項目要求，現為該項目徵求一顧問提供者（以下稱「 該顧問」）及其提議的服務，以協助澳電處理與該項目及相關土壤修復承辦商（以下稱「 拆卸承辦商」）的管理、合同執行及監督之事宜，以確保該項目能有質量地按時完成。

Based on above project requirements, a consultant provider (Hereafter called “the Consultant”) and its proposal for Consultancy services are requested to assist CEM in administering the contract and supervising the Project together with the Demolition and Soil Remediation Contractor (Hereafter called “Demolition Contractor”), to ensure its quality and timely completion.

# 顧問服務範圍SCOPE OF CONSULTANCY SERVICES

服務範圍包括對該項目的拆卸及土壤修復現場工作進行仔細監督、實施及確保安全、環保及質量控制、監控施工進度以符合核准的工程計劃、識別工期延誤及超支風險並向澳電警示，及確保各項拆卸工作符合安全法規的要求。

The scope of service shall include detailed supervision of site activities for demolition and soil remediation, safety, environment & quality assurance and quality control of the Project, monitoring progress against the approved program, identifying and alerting CEM to potential time and cost overruns, and ensuring compliance with demolition safety regulations.

該顧問需往施工現場派遣具備相關專業資質的全職工程師或技術人員，或按要求聘請第三方專業人士以監督拆卸和修復工作。若聘用第三方專業人士，該顧問須對該專業人士的工作表現及一切行為負擔全部責任。該顧問在提供該監理服務期間，應自行承擔和管理所需的一切工具、交通、辦公設備及其他相關資源。

The Consultant shall deploy full-time in-house technical staff or engineers in the required disciplines, or engage third-party specialized personnel as needed, to supervise demolition and remediation activities. In the event that third-party specialized personnel are engaged, the Consultant shall retain full responsibility for their performance and actions. All tools, transportation, office equipment, and other resources necessary for the execution of the contracted supervision services shall be provided and maintained by the Consultant.

該顧問需實施的工作範圍為：

The scope of supply executed by the Consultant shall be:

- 審核施工方案：

制定拆卸方案的責任由拆卸承辦商承擔。該顧問應協助澳電，以專業技術角度對拆卸承辦商提交的方法和設計進行分析和審查。該顧問需就相關方案是否符合合同規格要求及現行行業的最佳實作標準向澳電發出評論，並在需要時提出恰當的審核及批准建議。

Methodology Review:

Methodology liability rests with the Demolition Contractor. The Consultant shall support CEM by reviewing submitted methodology and designs from a professional and technical standpoint. The Consultant shall advise CEM on compliance with contractual requirements and current industry best practices, and provide appropriate review comments and approval recommendations as necessary.

- 拆卸及土壤修復工作的監督

該顧問應監督工程的實施，確保所有工作均按合約條款、已核准的設計及施工方法進行。該顧問需針對主要工程事項制定和更新檢查記錄表，以記錄每次現場檢查時所發現的事宜。如有偏離合同要求或與核准設計出現偏差的情況，應即時識別和記錄，並向澳電報告。

該顧問在提供全職現場監督服務時，需調配足夠數量且具備具相關專業資質的工程師及技術人員，並確保有充足的現場駐守時間，以提供持續有效的監督效果。

Supervision Work for Demolition and Soil Remediation:

The Consultant shall supervise the execution of the works to ensure that all activities are carried out in accordance with the contract terms and conditions, as well as the approved designs and methodologies. The Consultant shall develop and maintain inspection checklists for major work items to document observations during each site inspection. Any deviations from the contractual requirements or approved designs shall be promptly identified, recorded, and reported to CEM.

For full-time site supervision, the Consultant shall provide an adequate number of qualified technical staff and engineers across relevant disciplines, with appropriate on-site durations to ensure continuous and effective oversight.

- 施工准照：

（如適用）有關拆卸承辦商與澳門相關權限實體所進行的施工准照申請流程，該顧問亦需跟進和協調。

Work Permit and License:

If applicable, the Consultant shall be responsible for follow-up and coordination of all actions undertaken by the Demolition Contractor in relation to the licensing process with the Macau Authorities.

- 施工材料：

該顧問應檢查並確保該項目中所有使用的材料均已進行測試，且符合合同要求及澳門現行法例。該顧問須妥善保管所有測試報告，以供日後查閱和審核之用。

Materials:

The Consultant shall inspect and ensure that all materials used in the Project are tested and comply with the contractual requirements and applicable Macau legislation. The Consultant shall maintain records of all such test reports for review and audit purposes.

- 質量保證及控制：

該顧問應進行巡查及監督，確保工程按照已批准的設計、方法、合同技術規格、相關技術標準，以及適用的澳門法律法規而執行，包括但不限於：

- 監察拆卸承辦商每日的現場施工活動；

- 記錄各項施工活動每日的實際情況；

- 對所有執行的工程進行品質監管、質量檢測及現場檢查；

- 澳電項目經理保持溝通和每日進行報告，及時反映在拆卸、修復等工作中出現的問題、偏差或需要的變更；

- 出席各工程項目會議。

Quality Assurance and Control:

The Consultant shall inspect and ensure that the Project are carried out in accordance with the approved designs, methodology, contractual specifications, relevant technical standards, and applicable Macau legislation, including (but not limited to):

- To monitor all site activities of Demolition Contractor in daily basis;

- To keep notes on daily basis of all site activities;

- To conduct quality assurance, control tests and inspections for all works preformed;

- To communicate in daily basis with CEM’s Project Manager regarding any concerns, discrepancies or alterations that may arise during the course of demolition,  and relevant activities;

- To attend progress meetings.

- 人員、機械及設備需求：

該顧問應監督各執行單位的現場安排是否充足，包括技術及監督人員、施工人員、機械設備的配置與到位情況、材料採購和其他資源的調配，以確保工程能依照批核的工程計劃按時完成。該顧問需編制和更新每日報告，記錄人員、機具、設備及施工材料等的調派情況。

Labor, Machinery, and Equipment Requirement:

The Consultant shall monitor the adequacy of the on-site setup established by the executing agencies, including the availability and deployment of technical and supervisory staff, labor force, machinery and equipment, material procurement, and other relevant resources, to ensure timely completion of the works in accordance with the approved schedule. The Consultant shall maintain daily reports documenting the utilization of labor, plant, equipment, and materials etc..

- 施工行程監察：

該顧問應監察各工程項目的進度，定期編制項目進度監察報告，並建議恰當的方法與措施以確保預定項目進度的達成。

Progress Monitoring:

The Consultant shall monitor the progress of various works on site, prepare regular progress reports, and recommend appropriate methods and measures to achieve the targeted work progress.

- 安建環：

該顧問應確保拆卸承辦商在工地現場有效地執行澳電的健康、安全及環境（HSE）政策、環境影響評估（EIA）報告中規定的各項措施，以及適用的法律法規要求，並進行每週巡檢、填寫檢查清單、報告不合規事項和記錄事故的發生，並採取適當的跟進措施。

Health, Safety and Environmental:

The Consultant shall ensure the effective implementation of CEM’s Health, Safety, and Environmental (HSE) policies, measures required and stated in the Project EIA report and applicable legal requirements on site. This includes conducting weekly inspections, completing inspection checklists, reporting non-conformities and incidents, and taking appropriate follow-up actions.

- 項目進度報告及項目會議：

該顧問應出席定期的項目會議，提交每月進度報告，並匯整先前報告所記錄已完成的工作。報告中需對可能影響項目執行成本或完工時間的重點問題進行評估。每份月度報告應包括記錄已執行的工作、運至工地的設備及材料供應的統計資料，並附上以下文件：

- 拆卸工程進度的統計；

- 有關修復、修改及搬遷工作的土方、混凝土、物料的質量測試結果，以及整個項目所使用設備的相關測試資料；

- 施工人員統計；

- 拆卸、修復、修改及搬遷工作相關的驗收測試報告；

- 施工期間遇到的問題記錄，及該顧問所提出的建議；

- 工程進度的現場照片記錄。

Progress Reports and Meetings:

The Consultant shall attend regular Project Review Meetings and submit monthly progress reports that review the work completed since the previous report. The reports shall include an assessment of all outstanding issues likely to impact the project’s cost or completion schedule. Each monthly progress report shall present statistical data on works executed, equipment delivered, and materials supplied to site, and shall include the following attachments:

- Statistic of demolition progress;

- Quality tests on earthworks, concrete works, materials in relevant remediation, modification and relocation works, together with the used equipment in whole project;

- Labor force statistics;

- Acceptance tests of demolition, remediation, modification and relocation;

- Records of problems encountered, and recommendation made by the consultant;

- Photographs recording the progress of work.

- 拆卸承辦商施工進度證書

該顧問需審查、驗證和確認拆卸承辦商所報告的工作進度，以就澳電可否發出施工進度證書提供建議。

Certification of Work Progress of Demolition Contractor:

The Consultant shall review, verify, and confirm the work progress reported by the Demolition Contractor as a prerequisite for CEM to issue the Certificate of Work Progress.

- 可回收廢棄物料的統計監督：

該顧問應檢查、統計並監控拆除工程中可回收廢棄物料（如廢棄銅線、設備鐵料等）的種類與數量，同時確認秤重設備的準確性，包括但不限於：

- 派駐現場人員並配備必要的檢測設備，以監督車輛及可回收物料的秤重作業。檢查、見證及記錄所有車輛、回收物料磅秤的調試和校準工作，確認磅秤秤重準確；

- 檢查及確認拆卸承辦商運出的可回收廢棄物料符合其申報的物料類型與數量，並進行記錄存檔；

- 檢查、監控和報告拆卸承辦商（包括其分包商、工作人員）是否違反物料回收相關的拆除工程合同條款，在無申報的情況下運出可回收物料；

- 對拆卸承辦商所實施的回收物料分類、秤重方式和安排等相關事宜進行評價，並提供改善建議；

- 依據拆除工程合同條款及投標報價，對統計所得的回收物料數量進行核算，並評估其價值。

Statistical Oversight of Recyclable Waste Materials

The Consultant shall inspect, tally, and monitor the types and quantities of recyclable waste materials (e.g., scrap copper wire, ferrous equipment components, etc.) generated during the demolition works, and verify the accuracy of all weighing equipment. This includes, but is not limited to:

- Deploy on-site personnel equipped with necessary inspection instruments to monitor the weighing of vehicles and recyclable materials;

- Inspecting, witnessing, and documenting the calibration and adjustment of all weighbridges and scales used for recyclable materials to ensure measurement accuracy;

- Verifying that the types and quantities of recyclable waste materials removed by the Demolition Contractor match their declared records, and maintaining documented evidence thereof;

- Monitoring and reporting any breaches by the Demolition Contractor (including its subcontractors and personnel) of the demolition contract provisions related to material recovery—particularly unauthorized transportation of recyclable materials off-site without prior declaration;

- Evaluating the Contractor’s practices regarding the segregation, weighing procedures, and logistical arrangements for recyclable materials, and providing recommendations for improvement where necessary.

- Reconcile the quantities of recovered materials and assess their value based on the terms of the demolition contract and the Demolition Contractor’s tender pricing.

- 完工文件的驗證

該顧問應核實拆卸承辦商提交的竣工文件，確保其準確性、完整性，並己按核准的設計方案及合同要求進行編制。

Verification of As-built Documents:

The Consultant shall verify the “As-Built” document submissions provided by the Demolition Contractor for accuracy, completeness, and compliance with the approved designs and contractual requirements.

- 最終報告：

該顧問應在該項目和/或合同規定的顧問服務完結時，提交最終報告。

Provision of Final Report:

The Consultant shall submit a final report upon completion of the Project and/or the contractual consultancy services.

- 記錄：

該顧問應編製並妥善保管與該項目相關的文件之完整記錄，包括會議紀要、施工照片、測試及驗收報告、質量檢驗記錄、健康、安全與環境（HSE）巡查報告、不合規事項及事故發生記錄、缺陷清單，以及其他與該項目相關的文件。

此外，該顧問應開設現場指示記錄冊（Site Instruction Book）並進行更新，以記錄在現場巡查或工程執行期間，由澳電或該顧問向拆卸承辦商所發出的現場指示。

Records:

The Consultant shall prepare and maintain comprehensive records of all meeting minutes, progress photographs, test and commissioning reports, quality inspection records, Health, Safety, and Environmental (HSE) inspection reports, non-conformity and incident reports, defect lists, and other relevant project documentation.

In addition, the Consultant shall maintain a Site Instruction Book to formally record all instructions issued to the Demolition Contractor by CEM or the Consultant during site inspections or project execution.

- 檢查及測試：

該顧問應按需發起及協調現場巡查，以釐清設計和規格的細節要求。在項目實施的過程中，該顧問需定期檢查使用的材料及施工工藝，並見證或參與驗收測試，以確保施工結果滿足合同要求。若發現現場施工效果未能滿足規定的要求，該顧問應立即發出糾正建議，並確保拆卸承辦商展開整改工作。

Inspection and Test:

The Consultant shall coordinate site inspections as necessary to clarify design and specification details. Throughout all stages of implementation, the Consultant shall conduct regular inspections of materials and workmanship, as well as witness or carry out acceptance tests, to ensure compliance with contractual requirements. Where site works fail to meet the specified standards, the Consultant shall promptly recommend corrective actions and ensure that rectification is initiated.

- 缺憾處置：

如發現拆卸承辦商的施工結果存在缺陷，該顧問應將這記錄在缺陷記錄冊中。該顧問需向拆卸承辦商發出糾正指示，說明所需的整改措施，並對整改的執行情況進行檢查，以確保該缺陷及時清除，以符合合同要求。

Defects Handling:

In the event that any defects are identified in the work carried out by the Demolition Contractor, the Consultant shall record them in the Defects Register. The Consultant shall advise and instruct the Demolition Contractor on the necessary corrective actions and shall audit the implementation of rectifications to ensure they are completed promptly and in accordance with contractual requirements.

# 顧問的職責ROLES AND RESPONSIBILITIES

該顧問應以謹慎態度、有效率及成本效益，基於普遍應用的專業標準與實作，運用良好的管理原則，提供本合同規定的服務及履行所需義務。該顧問在與本顧問合同服務相關的一切事宜中，需始終以作為忠實顧問的角色為澳電提供意見，並在與第三方的往來中，持續支持並維護澳電的合法權益。

The Consultant shall perform the Services and fulfill all obligations with due diligence, efficiency, and economy, in accordance with generally accepted professional standards and practices, and shall apply sound management principles. The Consultant shall act at all times as a faithful advisor to CEM in all matters relating to this Consultancy Contract and the Services, and shall consistently support and protect CEM’s legitimate interests in any dealings with third parties.

項目管理、拆卸及土壤修復的現場監督與質量控制管理的工作，應涵蓋執行此類顧問工作的過程中通常要求的職能與工作內容。在該項目工程完結前，該顧問須全面履行下列各項所需的顧問工作及專業範疇內的支援：

- 工程諮詢

- 最終驗收與批准

- 拆卸工地的工程監督

- 項目質量保證與品質控制

- 健康、安全與環境管理

- 工程進度的規劃與管控

- 預算控制

- 測試與驗收

- 移交程序的監察

- 保固期內缺陷處理及後續跟進建議

- 索償管理

The Project Management, Demolition & Soil Remediation Site Supervision, and Quality Control Consultancy Services shall encompass all functions and activities typically required for the execution of this type of consultancy contract. The Consultant shall be responsible for fully carrying out all necessary tasks, covering the following activities and disciplines, through to the final completion of the Project:

- Engineering

- Final Approval

- Demolition Site Works Supervision

- Quality Assurance and Quality Control of the Project

- Health, Safety and Environmental Management

- Planning

- Budget Control

- Testing and Commissioning

- Taking-over Process

- Defects and Follow-up in Guarantee Period

- Claim Management

在該項目執行期間，該顧問需確保拆卸承辦商按照澳電及合同文件的要求，以執行施工及履行所要求的義務。凡涉及施工方案和設計的變更，以及技術問題討論之事宜，該顧問應適時向澳電提出專業建議，以作為審核與批准之依據。該顧問需作為澳電項目團隊的一員，參與並支援該拆卸工程和相關的修復、修改及搬遷工作的組織與管理，協助進行項目合同的行政管理工作，確保項目整體能順利推進。

During the implementation of the Project, the Consultant shall be fully responsible for ensuring the proper execution and fulfillment of the Demolition Contractor’s obligations in accordance with CEM’s requirements and the Project’s contract documents. The Consultant shall refer all matters relating to methodology / design changes and technical issues to CEM, accompanied by recommendations for approval, as and when necessary. The Consultant shall act as a member of the CEM’s Project Team, supporting the organization and management of demolition, together with relevant remediation, modification and relocation activities, and assisting in the administration of the project contract.

# 顧問組織人員的要求PERSONNEL OF THE CONSULTANT ORGANIZATION

該顧問需委派有資深技術背景且經驗豐富的專業人士，以支援該拆卸工程和相關整治、修改與搬遷工作能順利執行。委派的專業人士需具備以下專業領域的實務專長：

- 顧問／監理項目經理及監督人員

- 土木工程師

- 環境工程師（尤其專精於土壤修復工程）

- 機械或機電工程師

- 安全與安保工程師

- 其他所需的專業人員

The Consultant shall provide skilled and experienced personnel with demonstrated expertise in the following disciplines to support the successful execution of the demolition together with relevant remediation, modification and relocation works:

- Consultancy Project Manager and Supervisors

- Civil Engineer

- Environmental Engineer (Especially specializing in soil restoration works)

- Mechanical or E&M Engineer

- Safety and Security Engineer

- Others

除非經澳電書面同意，否則該顧問不得在顧問服務供給期間更換關鍵人員。若該顧問因無法控制的原因而需更換關鍵人員，該顧問應立即提議具備同等或更高資格與經驗的專業人員作為替代。任何情況下該顧問仍需確保服務品質始終維持在應有水平，不得因團隊人員變動而受到影響。

Except as otherwise agreed in writing by CEM, no changes shall be made to the Key Personnel during the provision of the consultancy service. Should it become necessary to replace any Key Personnel for reasons beyond the Consultant’s reasonable control, the Consultant shall promptly propose a replacement with equivalent or superior qualifications and experience. In all cases, the Consultant shall remain fully responsible for ensuring that the quality of the services is maintained at all times.

顧問團隊及監督人員須於工地全職駐場工作。顧問應為所有現場人員設立每日出勤記錄，並確保該記錄可應澳電要求時隨時提供查閱。

The Consultant team and supervisors shall be required to work full-time on site. The Consultant shall maintain a daily attendance register for all personnel at the worksite and ensure it is available for review by CEM upon request.

# 現場及檢查Site and Inspection

本服務及工程施工的實施地點位於中國澳門特別行政區路環發電廠A廠。

The location of the Services and the Site of the Works is at Coloane Power Station A in Macau SAR, China.

本顧問服務投標人需在投標階段親臨工程現場進行考察，以了解現場實際情況，並全面評估工地位置、進出通道、可用空間、設備性質、安全要求，以及可能影響監督執行或顧問投標方案編制的其他條件。

It is the responsibility of the Tenderer to visit the Site of the Works during the tender phase, to familiarize themselves with the site conditions, and to fully assess the location, access, available space, nature of equipment, safety requirements, and any other conditions that may affect the execution of the works or influence their tender submission.

該顧問需按接收施工現場時的實際狀況承接本服務，且不得以對工地情況不熟悉或因現場限制為由，提出任何追加費用或作出拖延。

The Consultant shall accept the Site in the condition it is found on the date of possession, without claim for additional cost or time due to unfamiliarity or site constraints.

# 顧問的供給DELIVERABLES BY THE CONSULTANT

- 該顧問需出席所有與拆卸承辦商討論的會議，並在有需要時另立會議以釐清技術、合同或施工執行的事宜。該顧問應持續監察工程的進度與質量，並在會議中告知所發現的問題，及提供相應的解決建議。

The Consultant shall attend all meetings with the Demolition Contractor and initiate additional meetings as necessary to clarify technical, contractual, or execution-related matters. The Consultant shall monitor the progress and quality of the works, and raise any issues or challenges for discussion, together with proposed solutions.

該顧問需負責編製會議紀要，跟進會議中所作出的決議、識別出的缺陷以及各方同意的糾正措施，確保其有效落實。

The Consultant shall prepare and issue meeting minutes, and ensure follow-up on decisions made, defects identified, and corrective actions agreed during the meetings.

工程進度會議應定期每兩週舉辦一次，如有需要，得增加會議密度。

Regular Progress Review Meetings shall be held at fortnightly intervals, or more frequently if required.

- 該顧問需作為澳電的技術代表。

The Consultant shall act as technical representative of CEM.

- 該顧問需審查和記錄下列（但不限於）資料及文件，並對澳電提供恰當的「核准」、「不批准」或「有條件接受」的建議。

- 拆卸承辦商的機具及設備；

- 拆卸方法及行程；

- 現場圍封及圍網的佈置，以及配置和運行大型拆卸設備所提供的安全措施；

- 環境控制措施，包括廢水排放管理、灰塵控制及噪音抑制計劃；

- 土壤修復方法及安排；

- 廢物處置流程；

- 拆卸後的現場修復方案。

The Consultant shall review, and as appropriate, approve, reject, or conditionally accept, and record, inter alia, the following:

- Demolition Contractor's plant and equipment;

- Demolition method and schedule;

- Site hoarding and fencing layout plan, together with safety measures for the setup and operation of large demolition equipment;

- Environmental control measures, including wastewater drainage management, dust control, and noise mitigation plan

- Methodology and arrangement to soil remediation;

- Waste disposal schedule;

- Post-demolition site recovery plan.

- 該顧問須審核拆卸承辦商所提交的施工方案，及提供是否核准的建議，以確保施工方案符合拆卸合同的要求和可安全進行，並核實其符合通用的行業標準與實作。

The Consultant shall review and recommend approval or non-approval decision to all method statements submitted by the Demolition Contractor to ensure compliance with the demolition contract, confirm that the works can be carried out safely, and verify adherence to recognized and accepted industry standards and practices.

- 在拆卸施工階段，該顧問需調派充足的技術人員持續監督，以確保有效地實施工程質量控制。該顧問必需在拆卸工程展開之前，派遣各級所需的具資質技術人員進駐現場。

During the demolition phase, the Consultant shall provide continuous supervision and sufficient technical personnel to ensure effective quality control of the works on site. Competent technical staff, as required at all levels, must be deployed by the Consultant prior to the commencement of any demolition activities.

該顧問需向澳電提交派駐工地現場的工程師／技術員的履歷，以供澳電審核及批准。

The Consultant shall submit the curriculum vitae (CV) of each engineer/technician proposed for deployment on site for CEM’s review and approval.

該顧問需指派維持一支具足夠人員及資格的技術團隊常駐工地，以對該項目持續地每日進行技術監督。監督和供給內容包括但不限於：

- 驗證工地佈局；

- 監控物料供給規格及是否準時採購；

- 確保施工遵從核准的設計、合同規格及接受的行業標準；

- 參與及見證供給的物料、結構或元件之現場測試；

- 參與及見證土壤修復工作中所需的取樣及現場測試；

- 提交項目進度報告；

- 如有需要，可提供所需額外工作的建議文件以供澳電判斷；

- 核證工程進度及安全、環保與質量控制措施；

- 支援項目最終檢查及交收流程。

The Consultant shall assign and maintain an adequate team of qualified technical staff at the worksite to carry out consistent and day-to-day technical supervision of the Project. This includes, but is not limited to:

- Verifying the site layout;

- Monitoring material specifications and timely procurement;

- Ensuring compliance with approved designs, contract specifications, and accepted industry standards;

- Conducting and witnessing field tests on materials, structures, and components;

- Conducting and witnessing sampling or field tests for soil remediation;

- Maintaining comprehensive site records, including supporting data and test results;

- Preparing and submitting progress reports;

- Recommending additional work items, where necessary, with documented justification;

- Certifying work progress and safety, environment & quality control measures;

- Supporting final inspections and handover processes.

以上所有工作均需以澳電規定及核准的表格形式進行記錄和文件化。

All such activities shall be documented using the forms prescribed or approved by CEM.

- 該顧問應確保拆卸承辦商已委託合資格實驗室，以進行與拆卸工程及土壤修復工作相關的樣本測試。該顧問需保存所有現場記錄，並確保相關支持資料已被記錄並經過核實。

The Consultant shall ensure that the Demolition Contractor properly entrusts qualified laboratories to conduct required sampling tests related to demolition activities and soil remediation works. The Consultant shall maintain all necessary site records and ensure that supporting data are duly recorded and verified.

如有需要，該顧問應評估現場狀況，並提出適當的改進建議，以確保工程符合設計、安全及環境標準。

Where necessary, the Consultant shall assess site conditions and recommend appropriate improvement to the works to ensure compliance with design, safety, and environmental standards.

- 該顧問應與澳電委聘的其他專業人員（包括但不限於工程師、建築師、環境專家及項目經理）保持緊密協調，以確保各項工作順暢銜接，各成員獲得資訊同步，使有效推進項目順利交付。

The Consultant shall ensure close coordination with all other professionals appointed directly by CEM, including but not limited to engineers, architects, environmental specialists, and project managers, to ensure seamless integration of activities, consistency of information, and effective project delivery.

- 該顧問應運用適當的規劃與控制工具監控項目進度。每月需編製進度報告，詳細列明已完成的工作內容，並對比實際進度與預先設定的目標，評估整體項目執行情況。

The Consultant shall monitor project progress using appropriate planning and control tools. Monthly progress reports shall be prepared, detailing the work executed and comparing actual progress against pre-established targets.

該顧問應定期檢查工程進度是否貼合施工計劃與項目整體行程。如有工程延誤的風險，該顧問需提出糾正措施和改善建議，以確保工程能按時完成。在項目執行期間，該顧問應每月向澳電提交項目進度報告。

The Consultant shall conduct regular reviews of progress in relation to the current schedule and overall project timeline. Where necessary, the Consultant shall propose corrective actions and improvements to ensure timely completion. A comprehensive monthly progress report shall be submitted to CEM throughout the duration of the works.

- 該顧問需確認拆卸承辦商完成的工作已滿足合同要求，並向澳電建議是否能發出工作完成證書。

The Consultant shall verify the completion of the works and, upon satisfaction that all contractual requirements have been fulfilled, recommend the issuance of the Completion Certificate to CEM.

- 該顧問應對已完成及準備移交的工作進行檢查，編製缺陷清單，列出未完成或不滿足合同要求的事項，確保所需文件均已齊備並在正式移交前提交澳電。

The Consultant shall inspect the completed works that are ready for handover, prepare a defect list identifying any outstanding items or deficiencies, and ensure that all requisite documentation is compiled and submitted to CEM prior to formal handover.

- 該顧問應審核拆卸承辦商編制的風險評估、安全管理計劃、環境影響評估及環境管理計劃，並確認是否符合所有適用的法規、標準及澳電要求，並向澳電提議可否批予。該顧問需監察工地安全、施工人員實作及法律法規的遵從情況，並代表澳電向項目中出現的問題、違規或求詢進行適當處置。

The Consultant shall review the Risk Assessment, Safety Management Plan, Environmental Impact Assessment, and Environmental Management Plan prepared by the Demolition Contractor, and recommend their approval to CEM, ensuring compliance with all applicable codes, regulations, and CEM’s requirements. The Consultant shall monitor site safety, labor practices, and regulatory compliance, and shall take appropriate action on behalf of CEM in response to any issues, violations, or inquiries.

- 該顧問應制訂詳細的人力資源調配計劃，以列明該項目各階段應分配的顧問人員與資源，以滿足所規劃的項目需求。該顧問需釐清所需顧問資源的類別與數量，明確其進場時間，確保所有顧問資源於項目執行期間能按時到位。

The Consultant shall develop a detailed Manpower and Resource Deployment Plan, outlining the consultancy personnel and resources allocated to each phase of the Project to meet the planned project requirements. The Consultant shall identify the types and quantities of consultancy resources required, specify the timing for their deployment on site, and ensure that all consultancy resources are available as needed throughout the project duration.

# 機密性CONFIDENTIALITY

該顧問不得向第三方披露為澳電所編制或開發的任何資訊、數據、圖紙、方案、報告、規格、手冊或其他文件，亦不得在未經澳電事先書面同意的情況下，將上述資料用於與該項目無關之任何用途。此保密責任於本合約終止後仍然有效，並持續適用於所有機密資料。

The Consultant shall not disclose any information, data, drawings, method statements, reports, specifications, manuals, or other documents developed or prepared for CEM, nor shall such materials be used for any purposes unrelated to the Project without the prior written consent of CEM. This confidentiality obligation shall remain in effect after the termination of this Contract and shall continue to apply to all confidential information.

# 規範與限制REGULATION AND RESTRICTION

該顧問應遵守所有適用的法律法規和標準以提供顧問服務。

The Consultant shall comply with all applicable regulations in the provision of consultancy services on site.

所有顧問服務，包括提議的補救措施，均應在不導致發電廠停運的考量下進行；若停運是無法避免，則應將中斷運行的程度降至最低。任何可能導致設備或系統運行中斷的作業，必需先提交澳電進行審查及獲得批准。此類工作僅可在澳電明確同意後，並按照澳電指定的條件或時段內進行。

All consultancy-related activities, including proposed remedial actions, shall be carried out without causing disruption to the power plant’s operations, or, where unavoidable, such interruptions shall be kept to the minimum extent possible. Any work that may result in interruption to equipment or systems must be submitted to CEM for review and prior approval. Such work shall only be carried out with the explicit consent of CEM and under the specific conditions or timeframes directed by CEM.

# 服務供給期DURATION OF SERVICES TO BE PROVIDED

顧問服務涵蓋該項目各個階段，包括設計、拆卸前準備、拆卸中、土壤修復、驗收試運、項目移交接收以及缺憾／保修責任期。

The consultancy services shall be provided throughout all phases of the project, including the design, pre-demolition, demolition, soil remediation, commissioning, site handover (taking-over), and defect liability periods

- 現場工程與跟進Site Engineering and Follow-up

在該項目實施期間，連同相關的修復、修改及搬遷工作，提供技術支援和現場監督。

Providing technical support and site supervision during the implementation of the Project together with relevant remediation, modification and relocation works.

- 保修期間的缺陷修復Defects Remediation during Guarantee Period

大在項目實質完工後或缺陷責任期內，追蹤及監察所發現缺陷的整改工作。

Follow up the rectification of defects identified after substantial completion of the project or during the defect liability period.

# 一般要求GENERAL REQUIREMENT

- 顧問團隊需在該項目整個工程期間全職駐守工地；

- 需有充足人力資源，並根據該項目各階段的需要進行合理調配；

- 精通中文和英文，以確保與澳電項目團隊及拆卸承辦商現場人員的有效溝通；

- 與澳電及拆卸承辦商之間的所有文件及往來信函，均需以繁體中文及英文編製。凡合同規定需以書寫、標示、印刷或刻印方式呈現之資訊，均須以雙語呈現；

- 具備至少5年從事類似項目的土木、環境、機械/機電工程或安裝的經驗的人員；

- 具備至少5年土壤修復工程監督的經驗的人員；

- 具備至少5年於拆卸或相關項目之現場管理經驗的人員；

- 受過健康、安全及環境管理方面培訓的人員。

- The consultancy team shall be present on site on a full-time basis throughout the duration of the Project;

- Manpower shall be adequate and appropriately allocated to meet the requirements of each phase of the Project;

- Fluent in both Chinese and English to ensure effective communication with the CEM Project Team and Demolition Contractor site personnel.

- All documents and correspondences with CEM and the Demolition Contractor shall be prepared in Traditional Chinese and English. Wherever the Contract requires any information to be written, marked, printed, or engraved, it shall be presented in both languages.

- Minimum of 5 years’ experience in civil, environmental, and mechanical/Electrical & Mechanical (E&M) engineering or installation works on similar project.

- The Consultant shall have a minimum of 5 years of experience in the supervision of soil remediation works.

- Minimum of 5 years of site management experience on demolition or related projects.

- Be trained in Health, Safety, and Environmental (HSE) Management;

為確保項目管理的質量，該顧問的項目管理團隊需包括一名全職的項目經理。項目經理應為註冊或特許工程師，並在接受註冊／特許後具備至少10年的項目管理經驗。

In order to ensure the quality of project management, the Consultant’s project management team shall include a full-time Project Manager who is a chartered or registered engineer with a minimum of 10 years of post-charter experience in project management.

項目經理及其他關鍵團隊成員均需持有現行認可的專業資格，並與其專業範疇相符。

Both the Project Manager and other key team members shall hold current, recognized professional qualifications relevant to their respective disciplines.

顧問項目管理團隊（包括所有關鍵人員）的任命需經澳電批准，澳電有權根據人員的資格、經驗及適任性進行評估，並決定是否接納任何團隊個人。

The appointment of the Consultant’s project management team, including all key personnel, is subject to approval by the CEM, who reserves the right to assess and accept or reject any individual based on qualifications, experience, and suitability.

# 合同期限與後續服務TERM AND SUBSEQUENT SERVICES

本顧問服務合同之有效期為兩年（下稱「初始期限」）。

The validity period of this Consultancy Service shall be two (2) years (hereinafter referred to as the "Initial Term").

初始期限屆滿後，如澳電有意繼續聘用該顧問，雙方同意後續服務將依據報價單所列之後續每月費率標準計費，費用按月結算並支付。

Upon expiration of the Initial Term, should CEM intend to continue engaging the Consultant, the Parties hereby agree that subsequent services shall be billed in accordance with the subsequent monthly rate specified in the Quotation, with fees settled and paid on a monthly basis.

若後續服務期間實際工程監察範圍或工作量發生顯著變化，澳電有權提出調整月費之要求，顧問應予以合理配合並協商調整。在後續服務期間，任何一方均可提前 30 日 以書面通知終止服務。

In the event that the actual scope of engineering supervision or workload undergoes a material change during the period of subsequent services, CEM shall have the right to request an adjustment to the monthly fee, and the Consultant shall reasonably cooperate and engage in good faith negotiations with CEM to adjust the fee accordingly. During the term of subsequent services, either Party may terminate such services by providing thirty (30) days' prior written notice to the other Party.

# 施工真空期之處理Handling for the Construction Standby Period

本拆卸項目之現場既定工序，或會因下述審批程序原因而被迫暫停，從而形成施工真空期：

- 第一階段（主機組設備拆卸）：須待環保局對相關環境影響評估報告作出批准後，方可啟動相關拆卸工作；

- 第二階段（廠房樓宇拆卸）：須於取得工務局發出之拆卸工程准照後，方可開展相關工程；若第一階段設備拆卸已完成，而拆卸工程准照尚未獲發，現場工序將須暫停以待審批。

The predetermined on-site works sequence of the demolition project may be suspended due to the following approval-related reasons, thereby creating a construction standby period:

- Phase I (Main Equipment Dismantling): Commencement of the relevant dismantling works is contingent upon prior approval of the associated Environmental Impact Assessment (EIA) Report by the DSPA;

- Phase II (Plant Building Demolition): Commencement of the relevant demolition works is contingent upon receipt of the Demolition Works Permit issued by DSSCU. Should the Phase I equipment dismantling be completed while the Demolition Works Permit remains pending, on-site works shall be suspended pending approval.

考慮到在該施工真空期間，相關顧問監察的需求大大降低，該顧問須於報價中提供相應調減的替代方案，以安排至少一名合資格人員進駐，滿足施工真空期間最低的監察需求。服務範圍包括：

- 工地環境及安全管理；

- 拆卸方案的諮詢與評價；

- 工程及准照申請進度的跟進。

Given that the Consultant's supervision requirements are substantially reduced during this standby period, the Consultant shall provide a cost-adjusted alternative consultant proposal within their quotation. This proposal shall arrange for at least one qualified personnel to be stationed on-site to fulfill the minimum supervision requirements during the construction standby period, including:

- Site environmental and safety management;

- Consultation and evaluation of demolition methodologies;

- Follow-up on works progress and permit application status.

於施工真空期間，主體顧問服務將暫緩執行，並改以經調減之替代顧問服務方案實施。施工真空期不計入合約初始期限之履約計算；替代顧問服務之費用，將依據報價文件所列之相應每月費率標準計收，並按月結算及支付。

During the construction standby period, the principal consultant services shall be suspended, and the cost-adjusted alternative consultant service shall be implemented instead. The construction standby period shall be excluded from the calculation of the Initial Term of the Contract. Fees for the alternative consultant services shall be charged in accordance with the corresponding monthly rates specified in the quotation, and shall be settled and paid on a monthly basis.

施工真空期之啟動及終止，將由澳電以書面形式通知。

The commencement and conclusion of the construction standby period shall be formally notified by CEM in writing.

# 投標提交文件要求TENDER SUBMISSION REQUIREMENTS

13.1 技術標書 Technical Proposal

- 資格預審文件 Documents for Pre-Qualification

- 提交過去3年內沒有發生致命/嚴重工傷事故記錄之聲明書。

- 提交有效的商業登記證明。

- 提供M1和M8政府表格 (如非本地公司未在澳門財政局辦理相關表格，須提交保證書承諾於合同判給後1個月內提交)。

- 如投標者以合作經營／聯營體(JV)的方式構成，須提交相應各方簽署的諒解備忘錄 (MOU)。

- 提交參考項目之顧主所發出的項目完成證書及項目結算資料，以證明過去5年曾有在澳門完成合同金額達到或超過200萬元澳門幣的拆卸、建造或相類似工作的顧問合同之經驗，及具有財務及物料供給上的能力。

- 提供投標者已在工務局註冊工程監察職務之證據，或提供在本項目中僱用相關範疇專業的、具有工程監察職務之工務局註冊技術員的證據。

- 負責此顧問服務的團隊成員履歷 （與本章c) 點相同）。

- Tenderer's declaration stating that there has been no record of fatal / serious work-related accidents in the past 3 years;

- Available certification of commercial registration;

- M1 and M8 Government Form from Tenderer (if the company is not locally registered and has not completed the relevant forms with the Macao Financial Services Bureau, it must submit a letter of undertaking committing to submit them within one month of the contract being awarded);

- In case the Tenderers are form by means of Consortium / Joint-Venture (JV),  Tenderers shall submit corresponding signed Memorandum of Understanding (MOU) by both parties;

- Project Completion Certificates with information of project final accounts issued by previous clients of the reference projects, to prove Tenderer’s financial and material capabilities for completing consultancy service contract for demolition, construction, or similar works in Macau with contract amount on or greater than MOP2,000,000.00 for past 5 years;

- Evidence of Tenderer’s registration in the Land and Urban Construction Bureau of Macao SAR (DSSCU) for engineering supervision (工程監察) duties, or showing the employment of DSSCU registered engineer(s) in relevant discipline under engineering supervision (工程監察) duties;

- CV of each key team member in this Consultancy Service (as same to point d) in this Chapter).

- 建議書Proposal

該顧問應提交一份全面的提議書，以概述工程項目管理和監理諮詢服務的建議方案，包括但不限於：

- 對於該拆卸項目的了解及分析，須針對各項關鍵拆卸工序進行詳細分析，闡述監督工作的重點控制環節，並提交初步監督安排方案；

- 實施的顧問服務管理系統，及評估和監督計劃，包括其規劃、排程、報告和協調流程。須透過文字說明、監督控制流程圖、報告提交機制及現場記錄表單範本等方式，清晰闡述擬採用的監督管理系統；

- 就本規格第2章要求的顧問服務項目內所安排的人手、駐場與否，以及顧問服務中每一預料的拆卸階段內安排之總人數。

The Consultant shall submit a comprehensive proposal outlining the approach and methodology for delivering project management and supervision consultancy services, including but not limited to:

- Understanding and analysis of the captioned DDD project. Tenderers shall conduct a detailed analysis of each critical demolition activity, outline the key priorities for supervision, and submit a preliminary supervision arrangement plan.;

- Project Management Systems in place, and scheme of assessment & supervision plan,　including planning, scheduling, reporting, and coordination processes. Tenderers shall clearly elaborate on the proposed supervision management system through written descriptions, supervision control flowcharts, report submission mechanisms, and sample site record forms.

- The personnel, whether deployed full-time on-site for the consultant services required under Chapter 2 of this Specifications, and the total number of personnel assigned at each demolition stage/phase foreseen in the Consultant Services.

- 公司背景、組織架構圖和履歷Company Background, Organization Chart and Curriculum Vitae (CV)

- 公司簡介；

- 負責此顧問服務團隊的組織架構圖，以及每位主要團隊成員的履歷，包括主要人員的經驗與資質，包括其職責、關鍵能力、專業認證以及在相類似諮詢顧問服務案例中的過往記錄；

- 證明在澳門地區擁有充足的資源（如合法顧員、分判商合作伙伴），特別是熟識澳門工程准照辦理流程或具處理拆卸准照經驗之人員資源或合作伙伴；

- 採用質量控制和品質保證（QC/QA）體系、職業健康與安全 (OHS) 管理系統等的ISO（或其他等價的）認證證明；

- 聘用澳門本地工人的比例。

- Company introduction

- Organizational Chart of the consultancy team assigned to the Works, together with the CV of each key team member, with demonstration of experience and qualifications of the key personnel assigned, including their roles, key competencies, professional certifications, and track record in relevant project types.

- Demonstrated capability and availability of resources (e.g. legal employee, subcontractor) in the Macau regions, particularly personnel or partners who are familiar with the procedures for the work permits  or possessing handling experience for demolition licensesin Macau.

- Certification of ISO (or other equivalent) for the proof of adapting Quality Control and Quality Assurance (QC/QA) Systems, Occupational Health and Safety (OHS) Management System etc.

- Proportion of Macao local workers employed

- 參考資料Reference:

對以下參考經驗證明之提交，投標者須附上詳細說明，以證明具備相關專業知識、技術能力以及在類似作業環境或地區交付類似服務／項目的經驗。如引用合作夥伴之參考經驗，須提交有效合作證明（如協議或授權書）。

- 投標者近10年在澳門提供監督顧問合同額不少於澳門幣2,000,000元的拆卸或建造項目顧問服務之參考工作案例數量與清單；

- 投標者或其合作伙伴/分判商近10年在港澳、內地為包含樓宇或工業廠房土建拆卸工作之項目提供監督顧問服務的工作經驗數量與清單；

- 投標者或其合作伙伴/分判商近10年在港澳、內地為包含石棉構件、油污污染設施，或化學管道及相聯設備的拆卸或維修相關工作項目提供監督顧問服務的工作經驗數量與清單；

- 投標者或其合作伙伴/分判商近10年在港澳、內地為大型機械、機電設備的拆卸、維修或安裝工作相關之項目提供監督顧問服務的工作經驗數量與清單。

- 投標者或其合作伙伴/分判商近10年為供電事業機構或政府項目提供監督顧問服務之參考工作案例數量與清單。

Regarding the evidence of following job reference, Tenderer’s submission shall be accompanied by a detailed statement demonstrating the Consultant’s relevant expertise, technical capabilities, and proven experience in delivering comparable service / projects in similar sectors or geographical areas. Where reference is made to a partner's experience, valid proof of collaboration (e.g., agreement or authorization letter) shall be submitted.

- Number and list of Tender’s job reference to perform consultancy services for demolition or construction projects, with value of consultancy contract not less than MOP 2,000,000 in Macau in recent 10 years;

- Number and list of Tenderer or their partner/subcontractor's job experience of consultancy services for the projects including demolitions for buildings or industrial facilities in Macau, HK & Mainland China in recent 10 years;

- Number and list of Tenderer or their partner/subcontractor's job experience of consultancy services for the relevant projects including demolitions or maintenance for asbestos-containing structure, oil-contaminated facilities, or chemical piping system and associated equipment in Macau, HK & Mainland China in recent 10 years;

- Number and list of Tenderer or their partner/subcontractor's job experience of consultancy services for the relevant projects including demolitions, maintenance or installation for large-scale machinery and E&M equipment in Macau, HK & Mainland China in recent 10 years;

- Number and list of Tenderer or their partner/subcontractor's job experience to provide consultancy service to projects of Macau, HK & Mainland China's power supply industries or governments in recent 10 years.

- 安全及健康管理計劃 Safety & Health Management Plan:

- 填寫《澳電對服務供應商之安全、健康、環境及質量要求及責任規定》內之表格，並提供制定之安全計劃。

- Filling “CEM Safety, Health, Environment and Quality Requirements & Responsibilities for Services Suppliers”, and submit the safety plan proposed.

  - 商業標書 Commercail Proposal

- 價格 Prices

該顧問應根據所要求的顧問服務範圍提交總價及詳細的費用明細，涵蓋：

- 初始期限內主顧問服務之報價；

- 初始期限屆滿後之後續顧問服務之月費率；

- 施工真空期間之替代顧問服務月費率。

工程量清單的內容不得更改。若有替代方案，必須另行提供一份工程量清單。為評估替代方案，投標者須提交一份已消除價格的工程量清單，並將其附於技術標書中供審議。

The Consultant shall submit a total lump-sum price along with a detailed cost breakdown based on the defined scope of consultancy services, covering:

- Lump sum for principal consultant services during the Initial Term;

- Monthly rate for subsequent consultant services beyond the Initial Term;

- Monthly rate for alternative consultant services during the construction standby period.

The contents of the Bill of Quantities must not be altered. Should an alternative proposal be submitted, a separate Bill of Quantities must be provided. In order to evaluate the alternative proposal, tenderers must submit a bill of quantities with prices removed, and attach it to the Technical Proposal for consideration.

# 顧問服務期間需提交的文件DOCUMENTS TO BE SUBMITTED DURING THE CONSULTANTCY SERVICE

| 文件Documents | 時限Time Limit |
| --- | --- |
| 項目工程管理及監工諮詢服務項目 Project Management and Supervision Consultancy Services Program | 合同簽訂後第 15 天或以內提供，每月更新 15 days after contract with monthly update |
| 時間表 Time Schedule | 合同簽訂後第 15 天或以內提供，每月更新 15 days after contract with monthly update |
| 會議記錄 Minutes of Meetings | 不遲於每次會議結束後 2 天 Not later than 2 days after every meeting |
| 安全巡查記錄 Safety Inspection Records | 每週 weekly |
| 項目檢查記錄 Inspection Records | 必要時 As and when necessary |
| 質量管理記錄 Quality Control Records | 每週 weekly |
| 月度報告 Monthly Report | 月度總結，並於該月結束後 7 天內提供 Monthly – within 7 day s of month end |
| 中期報告 Mid-Term Report | 待定 TBA |
| 最終報告 Final Report | 待定 TBA |
| 合同規格所要求的其他報告和記錄 Other Reports and Records required in the specifications | 待定 TBA |

該顧問應審查、提供意見及提議是否批予拆除承辦商在工程實施期間所發出的施工文件，包括但不限於設計資料表、設計、施工方案、計算書和施工行程。此項審查應依照文件提交時間表、及澳電與拆除承辦商就該項目所達成的項目行程而進行。

The Consultant shall review, comment on, and recommend the approval or non-approval decision to all execution documents issued by the Demolition Contractor during the execution of the works, including but not limited to design data sheets, design, method statement, calculation sheets, and execution schedule. This review shall be conducted in accordance with the Document Submission Schedule and the agreed timeline established between CEM and the Demolition Contractor for the Project.

# 投標強制要求Compulsory Requirement

建議書必須符合以下所有強制性要求。任何不符合強制性要求的情況將導致投標者自動被取消資格：

- 投標人在與澳電相關的項目，沒有表現不佳的記錄；

- 投標人提交過去3年內沒有發生致命/嚴重工傷事故記錄之聲明書；

- 投標人需提交有效商業登記證明；

- 投標者須提供M1和M8政府表格，如投標者為非本地公司且未在澳門財政局辦理相關表格，須提交保證書承諾於合同判給後1個月內提交；

- 如投標者以合作經營／聯營體(JV)的方式構成，必須在投標書中清楚描述，並提交相應各方簽署的諒解備忘錄 (MOU)；

- 投標者需在過去5年曾有在澳門完成合同金額達到或超過200萬元澳門幣的拆卸、建造或相類似的顧問服務合同之經驗，以證明財務及供給上的能力。投標者需提交項目顧主所發出的項目完成證書及項目結算資料以作證明；

- 投標者需已在工務局註冊工程監察職務，或提供在本項目中僱用相關範疇專業、具有工程監察職務之工務局註冊技術員的證據；

- 投標者之團隊必須包括具有第10章要求之相關資歷專業技術人員。

- 投標者必須完全接受本規格第11章有關合同初始期限屆滿後之後續顧問服務的處理安排，並提供相關月費報價；

- 投標者必須完全接受本規格第12章有關施工真空期之處理安排，並提供相關月費報價。

The submitted Proposal must comply with the following compulsory requirements. Failure to meet any of these compulsory requirements shall result in the disqualification of the Tenderer:

- No record of unsatisfactory performance in CEM related projects;

- Tenderer's declaration stating that there has been no record of fatal / serious work-related accidents in the past 3 years;

- Tenderers must provide available certification of commercial registration;

- The tenderers must provide the M1 and M8 Government Form, if the tenderer is not locally registered company and has not completed the relevant forms with the Macau Financial Services Bureau, it must submit a letter of undertaking committing to submit them within one month of the contract being awarded;

- In case the Tenderers are formed by means of Consortium / Joint-Venture (JV),  this must be clearly stated on the Tenderer's Proposal with a corresponding signed Memorandum of Understanding (MOU) by both parties.

- Tenderer shall have the financial and material capabilities for completing supervisory consulting service contract for demolition, construction or similar works in Macau with contract amount on or greater than MOP2,000,000.00 for past 5 years. Tenderer shall submit the Project Completion Certificates with information of project final accounts issued by previous clients of such projects as evidence;

- Tenderer must be registered in the Land and Urban Construction Bureau of Macao SAR (DSSCU) for engineering supervision (工程監察) duties, OR shows the employment of DSSCU registered engineer(s) in relevant discipline under engineering supervision (工程監察) duties;

- Tenderer's team must include professional and technical personnel with relevant qualifications and experience as specified in Chapter 10 of this Specification.

- The Tenderer shall fully accept implementation arrangement for the subsequent consultant services beyond the Initial Term of the Contract, as stipulated in Chapter 11 of this Specification, and provide the quotation of respective monthly fee;

- The Tenderer shall fully accept implementation arrangement for the alternative consultant services during the construction standby period, as stipulated in Chapter 12 of this Specification, and provide the quotation of respective monthly fee.

# 報價之有效期Validity of the Offers

報價之有效期限為截標日後 90 天。

Offers shall remain valid until 90 days from the closing date.

# 缺憾責任期 Defect liability period

顧問完成兩年初始期限內顧問服務的交收及取得澳電發出的接收證書（Taking Over Certificate, TOC）或後續服務終止後（以較遲者為準）的 12 個月內，完成缺憾清單（Defect List）中所有未符合合同要求之整改工作。

The Consultant shall rectify all outstanding items in the Defect List within 12 months after the issuance of the Taking Over Certificate (TOC) for the completion of consultancy service in the initial 2-year term, or the termination of subsequent consultancy services, whichever is later.

# 違約金 liquidated damages

如因顧問責任導致未能按約定期限提交月度、中期或最終報告，須就每份報告之每個延誤日，支付相當於合同金額 0.5% 之違約金，累計總額以合同金額之 10% 為上限。

Should the Consultant fail to submit the Monthly, Mid-term, or Final Reports by the stipulated dates due to causes attributable to the Consultant, liquidated damages shall be levied at the rate of 0.5% of the Contract Amount per day of delay for each report. The total amount of liquidated damages shall not exceed 10% of the Contract Amount.

# 其他　MISCELLANEOUS

## 安全預防措施　Safety Precaution

該顧問應對參與該顧問服務的所有人員的安全負責，並應採取業界普遍應用的良好工程規範而訂立的安全預防措施。該顧問應遵守澳門特別行政區所有現行適用的健康、安全及環境法規，包括最新生效的第2/2023號法律。該顧問也應遵從最新版本的《CEM Safety, Health, Environment and Quality Requirements & Responsibilities for Services Suppliers （澳電對服務供應商之安全、健康、環境及質量要求及責任規定）》的要求。

The Contractor shall be responsible for the safety of all persons engaged in the execution of the consultancy works and shall take such safety precautions as are generally accepted as good engineering practice. The Contractor shall comply with all applicable health & safety and environment regulations of Macau SAR, including the recent enforcement of Lei no. 2/2023 (第2/2023號法律). The Contractor shall also fulfill the requirements of the latest version of “CEM Safety, Health, Environment and Quality Requirements & Responsibilities for Services Suppliers”.

該顧問應負責提供所需充足的安全設備，並對其進行維護。

Adequate safety equipment shall be provided and maintained.

## 財產保護Protection of the Properties

在服務實施過程中，該顧問應注意保護澳電現有的財產和設施。若該顧問對澳電現有的財產和設施造成任何損害，相關因修復和補救工作而產生的一切費用需由該顧問負責和承擔。

The Consultant shall protect all existing CEM’s properties and facilities, for which the Consultant shall be responsible and bear all cost incurred on making good and remedying any damage caused thereto.

## 合同語言Contractual Language

合同語言為繁體中文和英文。合同要求所需提交之所有文件，包括提案、意見書及最終諮詢成果，均需以該兩種語言進行編制和提交。

Both Traditional Chinese and English shall be the contractual languages. All documents issued during the contract period, including proposals, submissions, and final consultancy deliverables, shall be prepared and submitted in both languages as required.